# Immunization Microplanning Workflow — WHO RED + Gavi RED-Q

Living reference. Mirrored in-app at Develop Microplan → Guided Workflow. Last refreshed: 2026-06-28.This document is the canonical end-to-end immunization microplanning process for VaxPlan tenants. It harmonizes: WHO RED — Reaching Every District strategy (WHO/AFRO, 2008; revised 2017 & 2021 microplanning guide).WHO/Gavi RED-Q / REC — Reaching Every Community with Equity, the zero-dose / missed-communities operationalization of RED used in Gavi 5.0 and the Equity Accelerator.IA2030 — Immunization Agenda 2030 strategic priorities (SP1 coverage & equity, SP5 outbreaks, SP7 sub-national equity).WHO/UNICEF Joint Reporting Form (JRF) — the indicator set every country reports annually. The 12-step cycle below is what facility staff, district reviewers, and national EPI officers are expected to walk every year, in the same order, against the same evidence base.

## 1. The two strategies in one cycle

### 1.1 WHO RED — five operational components

| # | Component | What it means at the health facility |
| --- | --- | --- |
| 1 | Re-establish outreach services | Catalogue every community outside the static catchment and schedule fixed, outreach, or mobile sessions to reach them. |
| 2 | Supportive supervision | Quarterly on-site supervisory visits by the district team using a standard checklist; findings drive corrective actions. |
| 3 | Community links with service delivery | Named community focal points, dialogues, and demand-generation activities co-owned with the facility. |
| 4 | Monitoring for action | Wall chart + defaulter tracking + dropout (DTP1→DTP3, DTP1→MCV1) reviewed monthly with staff. |
| 5 | Planning and management of resources | Annual microplan with target population, session calendar, vaccines, cold chain, staffing, budget, mobilization — approved up the hierarchy. |

### 1.2 Gavi RED-Q / REC — four equity layers on top of RED

| Layer | Purpose | Operational implication in the microplan |
| --- | --- | --- |
| Identify missed communities | Find every settlement getting 0 or partial sessions | Reconcile DHIS2/JRF coverage with catchment village list; flag villages with no DTP1 session in the past 12 months. |
| Reach zero-dose children | Drive DTP1 coverage where it is 0 | Tag villages by zero-dose burden; prioritize outreach and mobile sessions there. |
| Monitor equity | Disaggregate coverage by community, sex, wealth, displacement status | Report sub-village level coverage, not just facility totals. |
| Measure missed-community indicator | Gavi 5.0 flagship indicator | Compute % of catchment communities with at least one immunization contact per year. |

## 2. Roles and the approval cascade

| Role | Authors microplan? | Reviews / approves |
| --- | --- | --- |
| facility_clerk | ✅ Yes | — |
| facility_in_charge | ✅ Yes | Submits to district |
| district_manager | ❌ Read-only | Approve / return at district level (Step 11) |
| provincial_coordinator | ❌ Read-only | Approve / return at provincial level (Step 11) |
| national_admin | ❌ Read-only | Final approval, lock for execution (Step 11) |

Authoring is restricted to facility staff by both the UI (canCreateSessionPlan in client/src/lib/permissions.ts) and the server (POST /api/sessions returns 403 for non-facility roles). District and above only review and approve.

## 3. The 12-step annual cycle

Each step lists: Purpose · What to do · Required output · VaxPlan module · Definition of done.

### Step 1 — Situation analysis & coverage review (RED 5, RED-Q "Monitor")

- Purpose. Understand last year's performance before planning next year.

- What to do. Pull DTP1, DTP3, MCV1, MCV2 coverage; dropout %; zero-dose %; stockouts; AEFI; sessions planned vs held.

- Required output. A one-page coverage & equity snapshot per facility, with sub-village breakdown.

- VaxPlan module. Dashboard + Reports + Standards Alignment.

- Done when. Last full year of DTP1/DTP3/MCV1 coverage has been reviewed by the facility in-charge.

### Step 2 — Catchment & population mapping (RED-Q "Identify")

- Purpose. Establish denominators for every community served.

- What to do. Confirm the catchment polygon; list every village, hamlet, IDP camp, school; assign each to fixed, outreach, or mobile delivery; capture target population by source (NSO, HMIS, WorldPop, community census).

- Required output. A geocoded community list with target-pop denominator and population source.

- VaxPlan module. Boundary Manager, Population, Map View.

- Done when. Every catchment community has a target population with a recorded source.

### Step 3 — Hard-to-reach & equity profiling (RED-Q "Identify" + "Reach")

- Purpose. Classify communities by access difficulty and zero-dose burden so the strategy reflects effort, not just distance.

- What to do. Score each village on distance, terrain, seasonal accessibility, insecurity; tag missed communities (no contact in past 12 mo) and zero-dose hotspots.

- Required output. HTR score per village + missed-community flag + zero-dose tag.

- VaxPlan module. Hard-to-Reach, Population.

- Done when. Every village has an HTR score and an equity tag.

### Step 4 — Service delivery strategy & session calendar (RED 1)

- Purpose. Decide how each community is reached and when.

- What to do. For each community pick fixed / outreach / mobile delivery; produce a 12-month rolling calendar with one session per delivery point; schedule special strategies for missed communities (catch-up, periodic intensification).

- Required output. A 12-month session calendar covering every catchment community.

- VaxPlan module. Routine Microplan (Session Planning) or SIA Campaigns.

- Done when. A microplan exists for the current quarter with at least one scheduled session per community.

### Step 5 — Workforce & teaming (WHO core element 6)

- Purpose. Match staff and team composition to the session calendar.

- What to do. Per session-day assign vaccinator(s), recorder, supervisor, volunteers; for SIA add team type (house-to-house / fixed post) and per-team daily target.

- Required output. Staffing plan tied to the session calendar.

- VaxPlan module. Session Day Plans (per-session staffing fields).

- Done when. Every scheduled session-day has at least one named vaccinator and the roster is visible in session-day planning.

### Step 6 — Vaccine, supplies & cold-chain forecast (WHO core element 4, EVM 2.0)

- Purpose. Forecast doses, diluents, AD syringes, safety boxes, and cold-chain capacity for the plan period.

- What to do. Apply wastage factors (BCG ~40%, MR/OPV ~25%, Penta/PCV ~11%, IPV/Rota ~5%) per antigen; size cold boxes, ice packs, carriers per session; verify storage capacity at facility level.

- Required output. Forecast table (doses + vials + supplies + cold-chain capacity).

- VaxPlan module. Vaccine Calculator, Stock Ledger.

- Done when. Vaccine forecast exists for every active antigen for the plan period, with cold-chain and stock readiness visible in Stock Ledger and Plan Health.

### Step 7 — Demand generation & social mobilization (RED 3, RED-Q "Reach")

- Purpose. Plan how communities are informed and mobilized for every session.

- What to do. Per session schedule the announcement channel (megaphone, religious leader, SMS), the named focal point, and the target group; pre-position IEC materials.

- Required output. A mobilization activity per session, with date and target group.

- VaxPlan module. Social Mobilization.

- Done when. Every scheduled session has at least one mobilization activity.

### Step 8 — Logistics & transport (WHO core element 5)

- Purpose. Make sure the team and vaccines arrive at the community.

- What to do. Per session-day record transport mode, distance, fuel, vehicle/boat/escort, and (where applicable) security clearance.

- Required output. Transport line per session-day.

- VaxPlan module. Session Day Plans (transport + fuel fields).

- Done when. Every scheduled session-day has a transport mode and an estimated distance.

### Step 9 — Budget with funding source (WHO core element 8, Gavi HSS)

- Purpose. Cost the microplan and tag every line to a funder.

- What to do. Itemize Personnel / Transport / Supplies / Per Diem / Cold Chain / Training / Communication; tag each line with funding source (Govt, Gavi, WHO, UNICEF, Other).

- Required output. Quarterly budget with at least one line per category and an explicit funding source.

- VaxPlan module. Budget Planning.

- Done when. Budget items exist for the quarter and at least Personnel + Transport + Supplies categories are populated with funding-source evidence where required by tenant policy.

### Step 10 — Supportive supervision plan (RED 2)

- Purpose. Schedule quarterly supervisory visits using a standard checklist.

- What to do. Per facility schedule at least one supervisory visit per quarter, name the supervisor, conduct the visit and capture the 12-item WHO RED checklist (Yes / No / N/A) plus findings and follow-up actions.

- Required output. Supervisory visit calendar with checklist scores and follow-up actions for the quarter.

- VaxPlan module. Supportive Supervision (/supervision), backed by the supervision_visits table.

- Done when. Every facility with sessions this quarter has at least one supervisory visit scheduled (or conducted) with scheduled Date in the current quarter.

### Step 11 — Approval cascade (RED 5)

- Purpose. Move the microplan from facility draft → district → provincial → national approval.

- What to do. Facility in-charge submits; each level reviews catchment coverage, denominators, session calendar, budget tags, and equity flags; final national approval locks the plan for execution.

- Required output. Approved microplan with an audit trail (who approved, when, comments).

- VaxPlan module. Approvals.

- Done when. Microplan has reached approval_status = approved at the facility's terminal review level (district/provincial/national depending on tenant policy).

### Step 12 — Execution, monitoring & quarterly review (RED 4 + RED-Q "Measure")

- Purpose. Run sessions, record what happened, and feed it back into the next quarter.

- What to do. Record doses given per session (Client Logbook); update wall chart; review defaulters and dropout monthly; re-rank missed communities every quarter; trigger a coverage survey after every SIA.

- Required output. Monthly tally + defaulter list + quarterly review note; trigger Step 1 again for next year.

- VaxPlan module. Client Logbook, Dashboard, Reports.

- Done when. At least one session this quarter has actual doses recorded, a defaulter review has been run, and a quarterly review note is saved.

## 4. Required indicators (WHO + Gavi + JRF)

These are the indicators a complete microplan must compute or feed into. Status is tracked in-app at Settings → Standards Alignment.

| Indicator | Source | Why it matters |
| --- | --- | --- |
| DTP1 / DTP3 / MCV1 / MCV2 coverage | WUENIC, JRF | Core EPI performance signal. |
| DTP1→DTP3 dropout % | WUENIC | Programme retention; RED 4 monitoring. |
| DTP1→MCV1 dropout % | WUENIC | Cross-antigen retention. |
| Zero-dose children (no DTP1 by 12 mo) | Gavi 5.0 flagship | RED-Q "Reach" target. |
| Under-immunized children (DTP1 yes, DTP3 no) | Gavi 5.0 | RED-Q "Reach" target. |
| Missed-community % (no session in past 12 mo) | Gavi 5.0 / RED-Q | RED-Q "Measure" indicator. |
| Sessions planned vs held | RED 5 / HMIS | Plan fidelity. |
| Stockout-days per antigen per month | JRF | EVM 2.0 E6 signal. |
| Actual wastage rate per antigen | JRF | EVM 2.0 E6 signal. |
| AEFI cases per 100k doses | JRF / IHR 2005 | Safety surveillance. |
| Cold-chain equipment functional % | JRF / EVM 2.0 | Capacity to deliver. |
| Supervisory visits completed vs planned | RED 2 | Quality assurance. |

## 5. Definition of a "complete" microplan

A microplan is complete (ready for approval submission) when all twelve of the following are true:

- The catchment has a denominator for every community with a recorded source (Step 2).

- Every community has an HTR score and equity tag (Step 3).

- A 12-month session calendar exists covering every community (Step 4).

- Every session-day has a named vaccinator (Step 5).

- A vaccine + supplies forecast exists for every active antigen (Step 6).

- Every session has a mobilization activity (Step 7).

- Every session-day has a transport mode and estimated distance (Step 8).

- The quarter's budget has Personnel + Transport + Supplies lines, each tagged to a funding source (Step 9).

- A supportive-supervision visit is scheduled for the quarter (Step 10).

- The microplan has been submitted for approval (Step 11).

- The approval has reached the tenant's terminal review level (Step 11).

- At least one session this quarter has actual doses recorded and a defaulter review has been run (Step 12).

VaxPlan now surfaces the full cycle through the guided workflow, dashboard Plan Health score, supervision, defaulters/dropout, and quarterly review coverage. Items that require tenant configuration remain visible as maturity recommendations in Standards Alignment.

## 6. Mapping table — step → VaxPlan module

| Step | Module(s) | Route(s) |
| --- | --- | --- |
| 1 | Dashboard, Standards Alignment | / , /standards-alignment |
| 2 | Boundary Manager, Population, Map View | /admin/boundaries , /population , /map |
| 3 | Hard-to-Reach, Population | /htr , /population |
| 4 | Routine Microplan, SIA Campaigns | /sessions , /sia-campaigns |
| 5 | Session Day Plans | /sessions/:id/day-plans |
| 6 | Vaccine Calculator, Stock Ledger | /vaccines , /stock |
| 7 | Social Mobilization | /mobilization |
| 8 | Session Day Plans | /sessions/:id/day-plans |
| 9 | Budget Planning | /budget |
| 10 | Supportive Supervision | /supervision |
| 11 | Approvals | /approvals |
| 12 | Client Logbook, Dashboard, Reports | /clients , / , /reports |

## 7. References

- WHO. Microplanning for Immunization Service Delivery using the Reaching Every District (RED) Strategy. WHO/AFRO 2009; revised 2017 and 2021.

- WHO. Reaching Every Community: Operational Guide for Immunization in Hard-to-Reach Areas. 2018.

- Gavi. Gavi 5.0 Strategy 2021–2025 and Equity Accelerator Framework.

- WHO. Immunization Agenda 2030: A Global Strategy to Leave No One Behind.

- WHO & UNICEF. Joint Reporting Form (JRF) on Immunization. Annual.

- WHO. Effective Vaccine Management (EVM) 2.0 Assessment Tool.